## UserStory
Requirement ID | Issue Type | Summary | Priority
REQ_MB_01 | Epic1 | Leasing a Commercial Property | High
REQ_MB_02 | Story1 | As a commercial property seeker, I want to sign up and login into magic bricks, so that I can view various property. | High
REQ_MB_03 | Sub story 1 | To sign up, I give details in magic bricks which will create an account for us. | High
REQ_MB_04 | Sub story 2 | I want to log in with my credentials, so that I can access property. | High
REQ_MB_05 | Story 2 | As a user, I want to navigate to the Commercial Properties section, so that I can specifically look for office spaces for lease. | High
REQ_MB_06 | Sub story 1 | I want to search office spaces by location, so that I only see properties in my preferred area | High
REQ_MB_07 | Sub story 2 | I want to apply filters (budget, size, furnishing, availability), so that I can narrow down the listings to match my needs. | High
REQ_MB_08 | Sub story 3 | I click search option to view the sorted results according to the filter. | Medium
REQ_MB_09 | Story 3 | As I got some desired property, I want to shortlist the property, so that I can choose the preferred property | High
REQ_MB_10 | Sub story 1 | I click heart icon so that I can add them to the shortlisted items. | Medium
REQ_MB_11 | Story 4 | As I want to know more details about the property I click view shortlisted items button | Medium
REQ_MB_12 | Sub story 1 | I click on the property again to see the more details | Medium
REQ_MB_13 | Sub story 2 | I want to validate whether the contact agent | Medium

## Test Scenario
TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of Test Cases | Test Case Details
TS_MB_01 | REQ_MB_01 | Verify that the url works consistently across different browsers (Chrome, Firefox, Edge). | Functional Testing | 2 | 1.To Check whether the url works in different browsers (Chrome,firefox,Edge).
TS_MB_02 | REQ_MB_02 | Verify that user can sign up by providing valid details. | Functional Testing | 1 | 1.The user gives valid Credentials (gmail, password).
TS_MB_03 | REQ_MB_03 | Verify that signed-in users can log in and view properties. | Functional Testing | 1 | 1.Valid login then the user lands on homepage.
TS_MB_04 | REQ_MB_04 | Verify that invalid users cannot log in. | Functional Testing | 3 | 1.No details are provided the in the login page. 2.Invalid login. 3.Invalid mobile number
TS_MB_05 | REQ_MB_05 | Verify that location filter works correctly. | Functional/UI | 2 | 1.Apply "Chennai" in location filter. 2.Apply "CasaGrand " in the project/location filter.
TS_MB_06 | REQ_MB_06 | Verify that location filter doesn’t work correctly. | Functional/UI | 2 | 1.Enter "Invalid Location " in location filter. 2.No location is provided.
TS_MB_07 | REQ_MB_07 | Verify whether the selected filter is applied | Functional/UI | 4 | 1. Move to commercial tab 2. Select the lease option 3. Select the Office space 4. Select budget for the property
TS_MB_08 | REQ_MB_08 | Verify that the result page have sort/shortlist | Functional/UI | 3 | 1. Click Sort By: Most Recent 2. Add to shortlist 3. Remove from shortlist
TS_MB_09 | REQ_MB_09 | Verify that the details of shortlisted property is present | Functional | 3 | 1. Click the view shortlisted property button 2. Click the property to know more about it

## Test Case
Test Case ID | Test Scenario | Precondition | Test Condition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status Iteration 1 | Actual Result Iteration 2 | Status Iteration 2 | Comments | Req: Reference
TS_MB_01_TC_01 | TS_MB_01 | Check whether Browser is installed. | Open Chrome | 1. Open Chrome 2. Enter MagicBricks URL 3. Press Enter | URL:https://www.magicbricks.com | Website loads successfully. | Website is loaded correctly. | Pass | - | - | The website is launched on the browser as expected.
TS_MB_01_TC_02 | TS_MB_01 | Check whether Browser is installed. | Open in firefox | 1. Open Firefox 2. Enter MagicBricks URL 3. Press Enter | URL:https://www.magicbricks.com | Website loads successfully. | In Firefox, page loaded slowly | Fail | Page loads fine after fix | Pass | Cross-browser verified
TS_MB_02_TC_03 | TS_MB_02 | User not registered. | Valid registration | 1. Go to Sign Up 2. Enter details 3. Click Submit | Email: roshinitestingproject@gmail.com Pwd: Magicbricks@20 | Account created & redirected | Account created successfully | Pass | - | - | Signup stable
TS_MB_03_TC_04 | TS_MB_03 | Valid account exists | Valid login | 1. Go to Login 2.Click on login with google account. | Email: roshinitestingproject@gmail.com Pwd: Magicbricks@20 | User lands on homepage | Logged in successfully | Pass | - | - | Login is stable and secure.
TS_MB_04_TC_05 | TS_MB_04 | User is on login page | Invalid mobile numer | 1. Go to Login 2.Click on login with mobile number | Phone number : +9999999999 | Error message "Invalid mobile number displayed" | Error message "Invalid mobile number displayed" | Pass | otp is sent | Pass
TS_MB_04_TC_06 | TS_MB_04 | Login page open | Blank/No credentials | 1. Go to Login 2. Leave fields blank 3. Click Login | - | Error “Username/Password required” | Error not shown | Fail | Error displayed | Pass | Fixed in Iteration 2
TS_MB_04_TC_07 | TS_MB_04 | Account exists | Invalid credentials | 1. Go to Login 2. Enter wrong password 3. Click Login | Email: roshinitestingproject@gmail.com Pwd: Magicbricks@20 | Error “Invalid credentials” | Error displayed | Pass | - | - | Handles negative test case correctly by showing errors
TS_MB_05_TC_08 | TS_MB_05 | Properties available User is on home page of Buy | Valid location input | 1. Open location filter 2. Enter “Chennai” 3. Click search | Chennai | Chennai properties displayed | Correct list displayed | Pass | - | - | Location filter works correctly
TS_MB_05_TC_09 | TS_MB_05 | Project exists User is on home page of Buy | Valid project input | 1. Open location filter 2. Enter “Baashyam” 3. Click search | Baashyam | Baashyam projects displayed | Results displayed | Pass | - | - | Project filter works correctly
TS_MB_06_TC_10 | TS_MB_06 | Properties available User is on home page of Buy | Blank location field | 1. Open location filter 2. Leave blank 3. Click search | - | No filtering applied | No change in list | Pass | - | - | Negative test case is handled correctly
TS_MB_06_TC_11 | TS_MB_06 | Properties available User is on home page of Buy | Invalid location | 1. Open location filter 2. Enter “Xyz123” 3. Click search | Invalid Location | Error message "Please enter a valid project/location should be displayed | No error message | Fail | Error message displayed | Pass | Bug could be present as initially failed
TS_MB_07_TC_12 | TS_MB_07 | Tab above the search bar is in Buy | Select the commercial tab | 1. Move the tab from buy to commercial 2. Select the commercial | - | Moves to the commercial tab | Moves to the commercial tab | Pass | - |  | -
TS_MB_07_TC_13 | TS_MB_07 | Filters are visible on screen. | User selects Lease filter. | 1. Click lease option if it is not present as default | - | Lease option is selected | Lease option is selected | Pass | - | Pass | Filter is working
TS_MB_07_TC_14 | TS_MB_07 | Filters are visible on screen. | User selects office space filter. | 1. Click Office Space option if it is not present as default | - | Office Space clicked | Office Space clicked | Pass | - | Pass | Filter is working
TS_MB_07_TC_15 | TS_MB_07 | Filters are visible on screen. | Enter Min and Max price range | 1. Select the budget filter 2. Enter Min value 3. Enter Max value | Min value - 1 Lac Max value - 1.5 Lac | Properties within budget range | Properties higher than max value is also visible | Fail | Properties higher than max value is also visible | Fail | Filter is working but less accurate
TS_MB_07_TC_16 | TS_MB_07 | Home page | Search button is clicked | 1. Search button is clicked | - | Filtered Result page | filtered result page | Pass | - | Pass | -
TS_MB_08_TC_17 | TS_MB_08 | Result page | Most Recent is selected | 1. Select the Sort By Dropdown 2. Choose the Most Recent Option | - | Filtered Result page | filtered result page | Pass | - | Pass | -
TS_MB_08_TC_18 | TS_MB_08 | Result page | Property exists | 1. Select property 2. Click “Add to shortlist” 3. Verify list | Property A | "Added to Shortlist" | Added successfully and is present on the shortlisted properties | Pass | - | Pass | Filter is working
TS_MB_08_TC_19 | TS_MB_08 | Result page | Property exists | 1. Open shortlist 2. Remove property 3. Verify removal | Property A | "Removed successfully" | Property is removed and is not present on the list. | Pass | - | Pass | Filter is working
TS_MB_09_TC_20 | TS_MB_09 | Result page | View shortlisted items | 1. Click the shortlist button in header 2. Click view properties button | - | Shortlisted property is present | Shortlisted property is present | Pass | - | Pass | Locator incorrect
TS_MB_09_TC_21 | TS_MB_09 | Shortlisted Page | Click to view more details | 1. Hover the card 2. Click the card 3. Validate whether the contact owner is present | - | Details of the card | Details of the card | Fail | - | Fail | Locator incorrect

## Defect Report
Defect Id. | Module name | Defect Summary | Defect Priority | Assigned To | Status
Def_01 | URL | URL is slow on firefox browser , page loads slowly | High | Dev Team | To Do
Def_02 | Sign up | The page does not redirect to signup page when the button is clicked. | High | Dev Team | To Do
Def_03 | Login | The page accepts invalid mobile number and no error message is indicated. | High | Dev Team | To Do
Def_04 | Filter | The page shows value out of the budget range | High | Dev Team | To Do
Def_05 | Filter | When min range modified then we cannot scroll down | Medium | Dev Team | To Do

## RTM
BR_ID | TS_ID | TC_ID | Status | DR_ID
BR_MB_01 | TS_MB_01 | TS_MB_01_TC_01 | Pass | DR_MB_01
|  | TS_MB_01_TC_02 | Pass
BR_MB_02 | TS_MB_02 | TS_MB_02_TC_03 | Pass | DR_MB_02
BR_MB_03 | TS_MB_03 | TS_MB_03_TC_04 | Pass | DR_MB_03
BR_MB_04 | TS_MB_04 | TS_MB_04_TC_05 | Pass | DR_MB_04
|  | TS_MB_04_TC_06 | Pass
|  | TS_MB_04_TC_07 | Pass
BR_MB_05 | TS_MB_05 | TS_MB_05_TC_08 | Pass | DR_MB_05
|  | TS_MB_05_TC_09 | Pass
BR_MB_06 | TS_MB_06 | TS_MB_06_TC_10 | Pass | DR_MB_06
|  | TS_MB_06_TC_11 | Pass
BR_MB_07 | TS_MB_07 | TS_MB_07_TC_12 | Pass | DR_MB_07
|  | TS_MB_07_TC_13 | Pass
|  | TS_MB_07_TC_14 | Pass
|  | TS_MB_07_TC_15 | Fail
|  | TS_MB_07_TC_16 | Pass
BR_MB_08 | TS_MB_08 | TS_MB_08_TC_17 | Pass | DR_MB_08
|  | TS_MB_08_TC_18 | Pass
|  | TS_MB_08_TC_19 | Pass
BR_MB_09 | TS_MB_09 | TS_MB_09_TC_20 | Pass | DR_MB_09
|  | TS_MB_09_TC_21 | Fail

## Summary
Project Name | Module Name | Total Cases | Total Passed | Total Failed | Total Executed | Pass Percentage | Fail Precentage | Complition Percentage
Magicbricks | Test Leasing a commercial property module | 21 | 19 | 2 | 21 | 90.47% | 9.52% | 100%